# Tool D: Pilot Metrics Tracker

The metrics tracker evaluates whether training reuse, SIV redesign, or EDC training recognition reduces unnecessary training burden while monitoring participant protection, data quality, inspection readiness, and site readiness. Metrics should include both efficiency and quality indicators so the pilot can demonstrate that training was better targeted, not simply reduced.

| Metric | Category | How to measure | Desired direction |
| --- | --- | --- | --- |
| Training hours per staff member / study | Efficiency | Baseline average vs pilot average | Reduction without quality signal |
| Percentage of prior training or competency evidence accepted | Reuse | Number accepted / number evaluated | Increase in accepted valid prior evidence |
| Duplicate evidence requests to site | Documentation burden | Number of separate evidence requests per site or study | Decrease |
| Reusable core readiness content reuse / recognition | Reuse | Number or percentage of staff who completed or had recognized reusable core readiness content instead of repeating equivalent content | Increase |
| Reusable content moved out of live SIV | SIV redesign | Number or percentage of slides/topics moved to reusable core readiness content, vendor/platform training, job aid/reference, or other appropriate delivery methods | Increase where appropriate |
| Live SIV time spent on study-specific risk | SIV focus | Percentage of live SIV agenda devoted to protocol-specific, role-specific, or risk-critical content | Increase |
| Recognition turnaround time | Operational speed | Days from evidence review to recognition decision | Decrease |
| CRA/study team training reconciliation time | Internal burden | Estimated hours or task log | Decrease |
| Site activation cycle time | Startup speed | Study-specific baseline vs pilot | Decrease where training is gating item |
| Training-related support inquiries | Clarity / usability | Count of support tickets or questions | Stable or decrease |
| SIV-related clarification burden | Clarity/usability | Number of follow-up questions, support requests, or retraining items after SIV | Stable or decrease |
| Data quality and timeliness | Data quality | EDC query rates, data correction rates, late or incomplete data entry, missed assessments | No adverse trend |
| Quality and readiness signals | Quality/readiness | Sponsor/CRO/site assessment of documentation completeness, audit/inspection-readiness concerns, training-related support inquiries, protocol deviations or data-quality signals where training is a plausible contributing factor, and site/CRA feedback on readiness | Improve, or no adverse trend |
| Documentation completeness for recognition decisions and retrievability of supporting evidence | Documentation and inspection readiness | Decision records complete and retrievable | Near complete |